## Sheet1
Specflow, BDD based Testing Automation
| Product | End Date | Completed % | InProgress
| Pulse Tech (435) | 2019-10-31 | 22.45% | 9%
| Response | 2019-11-14 | 0% | 0%
| Connect | 2019-11-27 | 0% | 0%
Name | Stories | Status | Start Date | Estimated End Date | Actual End Date | Complete % | Impediments
Abhishek | BDD creation ¦ Induction module | In Progress | 2019-08-06 | 2019-08-14 | 2019-08-14 | 25%
Neelam | Script Development ¦ Planned Jobs | In Progress | 2019-08-08 | 2019-08-08 | 2019-08-13 | 10%
Rahul | Script Development ¦ Inspection Module | In Progress | 2019-07-30 | 2019-08-12 | 2019-08-12 | 90%
Sushma | Script Development ¦ Utility Order | In Progress | 2019-07-30 | 2019-08-09 | 2019-08-09 | 88%
Sushma | Mailable Report ¦ extent report in attachment | In Progress | 2019-07-30 | 2019-08-09 | 2019-08-09 | 88%
Yash | Script Development ¦ Contractor Compliance Functionality Part 1 (7 scenarios) | In Progress | 2019-08-05 | 2019-08-09 | 2019-08-09 | 50%